## 1weilaiPlan
	Work Item	Owner	Date					Optional Day
Sprint 1			2015/7/6	2015/7/7	2015/7/8	2015/7/9	2015/7/10	2015/7/12
	refine api framwork	Frank
	write user registration, login,logout	Frank
	replace zen-web with django framework	Alex
	write login,register,CAPTCHA UI interfaces	Alex
	Write activity publish, edit api	Gary
Goal: user register, login, logout

Sprint 2			2015/7/13	2015/7/14	2015/7/15	2015/7/16	2015/7/17	2015/7/19
	Add family for registered user	Alex
	Add children and for registered user	Alex/Frank
	Learn and write Interfaces for MongoDB	Gary
	Refine activity api with mongo	Gary
	Refine sqlalchemy db module	Frank
	Refine communication between UI and API	Frank
	UI for Activity publish, edit, remove	Frank
	Deployment of MongoDB with salt	Frank
Goal: Activity publish, edit, remove. Add family and children for users

Sprint 3			2015/7/27	2015/7/28	2015/7/29	2015/7/30	2015/7/31	2015/8/2
	QR-code generatation	Alex
	User can checkin with QR-code	Alex
	User can apply to be a volunteer	gary
	Create news template for news edit and publish	Frank
	write news publish, edit remove api	Frank
	Add log and conf modules to code	Frank
	Role and permission management	Frank
	Investigating Cordova	All
Goal: News publish, edit, remove, apply for volunteer

Sprint 4			2015/8/3	2015/8/4	2015/8/5	2015/8/6	2015/8/7	2015/8/9
	User can apply to create a organization	Alex
	User can add members for organization	Gary
	import existing 1weilai data to database	All
	create cordova project and run the framework	Frank
	Investigating Push Service	Frank
Goal: Organization Management(setup, add new member)

After sprint 4, the first edition for Hanxiao should be almost be ready

Sprint 5			2015/8/10	2015/8/11	2015/8/12	2015/8/13	2015/8/14	2015/8/16
	write push service	Frank
	Dashboard Dev Phase 3	Bryan
	Dashboard Sharing P1	Bryan
	Spark Modeling Dev	David
Goal: Show dashboard with runtime data, dashboard sharing demo

Sprint 6			2015/8/17	2015/8/18	2015/8/19	2015/8/20	2015/8/21	2015/8/23
	Setup Production Env	David,XiaoMing
	Data Collecter – CSV	David
	Production online testing	XiaoMing, Bryan
Goal: Production Env online

Sprint 7			2015/8/24	2015/8/25	2015/8/26	2015/8/27	2015/8/28	2015/8/30
	Business Requirement Define	Bryan,David
	Data Collect Base on Req	David
	Spark Modeling Dev	David,XiaoMing
	Dashboard Dev	Bryan
Goal: Dashboard demo, Production env demo

Sprint 8			2015/8/31	2015/9/1	2015/9/2	2015/9/3	2015/9/4	2015/9/6
	Business Requirement Define	Bryan,David
	Data Collect Base on Req	David
	Spark Modeling Dev	David,XiaoMing
	Dashboard Dev	Bryan
Goal: Dashboard demo, Production env demo

After sprint 8, all function should be almost be ready

Sprint 9			2015/9/7	2015/9/8	2015/9/9	2015/9/10	2015/9/11	2015/9/13
	Business Requirement Define	Bryan,David
	Data Collect Base on Req	David
	Spark Modeling Dev	David,XiaoMing
	Dashboard Dev	Bryan
Goal: Dashboard demo, Production env demo

Sprint 10			2015/9/14	2015/9/15	2015/9/16	2015/9/17	2015/9/18	2015/9/20
	Business Requirement Define	Bryan,David
	Data Collect Base on Req	David
	Spark Modeling Dev	David,XiaoMing
	Dashboard Dev	Bryan
Goal: Dashboard demo, Production env demo

Sprint 11			2015/9/21	2015/9/22	2015/9/23	2015/9/24	2015/9/25	2015/9/27
	Business Requirement Define	Bryan,David
	Data Collect Base on Req	David
	Spark Modeling Dev	David,XiaoMing
	Dashboard Dev	Bryan
Goal: Dashboard demo, Production env demo

After sprint 11, project released to customer

## Sprint2 Task Details
Sprint 2	Tasks	Owner	Description
	Add family for user	Alex	用户注册之后，添加
	Add children for user	Alex/Frank	用户注册之后，需要添加孩子信息．孩子信息的添加由工作 / 人员完成．
	Learn and write Interfaces for MongoDB	Gary	用pymongo编写mongo接口，连接池
	Refine activity api with mongo	Gary	api调用sqlalchemy, mogon借口操作数据库
	Refine sqlalchemy db module	Frank	定义db api接口，按照neturn & nova 代码 / 封装model 以及api接口
	Refine communication between UI and API	Frank	从zen-web call API接口, 封装connection / 连接池，call api to get session
	UI for Activity publish, edit, remove	Frank	UI:设计活动发布编辑ＵＩ
	Deployment of MongoDB with salt	Frank	编写salt 脚本部署Ｍongo