## 工作表1
	Work Item	Owner	Date
Sprint 1			2015/7/6	2015/7/7	2015/7/8	2015/7/9	2015/7/10	2015/7/12
(One week)	Setup Hardware env	XiaoMing, David
	Setup Salt env	David
	Business Requirement Define	Bryan,David
	DevOps Env Setup(Git, Gerrit, Jenkins, Ldap)	David
	Dashboard Dev Phase 1	Bryan
Goal: Spark and Hadoop online, show dashboard with real data, account management demo

Sprint 2			2015/7/13	2015/7/14	2015/7/15	2015/7/16	2015/7/17	2015/7/19
(One weeks)	Setup Hardware env	XiaoMing, David
	Setup Salt env	David
	Business Requirement Define	Bryan,David
	DevOps Env Setup(Git, Gerrit, Jenkins, Ldap)	David
	Dashboard Dev Phase 1	Bryan
Goal: DevOps online, show dashboard base on business requirement with fake data.

Sprint 3			2015/7/27	2015/7/28	2015/7/29	2015/7/30	2015/7/31	2015/8/2
	BigData Platform – Spark + Hdoop	David
	Dashboard Dev Phase 2	Bryan
	Data Collecter – MySQL	David
	Account Management	Bryan

Goal: Spark and Hadoop online, show dashboard with real data, account management demo

Sprint 4			2015/8/3	2015/8/4	2015/8/5	2015/8/6	2015/8/7	2015/8/9
	BigData Platform – Spark + Hdoop	David
	Dashboard Dev Phase 2	Bryan
	Data Collecter – MySQL	David
	Account Management	Bryan
Goal: Spark and Hadoop online, show dashboard with real data, account management demo

Sprint 5			2015/8/10	2015/8/11	2015/8/12	2015/8/13	2015/8/14	2015/8/16
	Business Requirement Define	Bryan,David
	Dashboard Dev Phase 3	Bryan
	Dashboard Sharing P1	Bryan
	Spark Modeling Dev	David
Goal: Show dashboard with runtime data, dashboard sharing demo

Sprint 6			2015/8/17	2015/8/18	2015/8/19	2015/8/20	2015/8/21	2015/8/23
	Setup Production Env	David,XiaoMing
	Data Collecter – CSV	David
	Production online testing	XiaoMing, Bryan
Goal: Production Env online

Sprint 7			2015/8/24	2015/8/25	2015/8/26	2015/8/27	2015/8/28	2015/8/30
	Business Requirement Define	Bryan,David
	Data Collect Base on Req	David
	Spark Modeling Dev	David,XiaoMing
	Dashboard Dev	Bryan
	API Dev ? (unclear req)	Bryan,David
Goal: Dashboard demo, Production env demo